## Sheet1
Sr No | Task
1) | Understanding Lambda Integration in Project
2) | Checking Customer API workfllow
2) | Updating Customer data at Code Level
3) | Updating Promo Code Table
4) | Validating abd re-building the solution
|  | Status |  |  |  | Remaining on
Sr No | Task |  | Est (in Hrs) | Start Dt | End dt | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21
1 | Understanding Lambda Integration in Project | Done | 5 Hr | 2022-05-09 | 2022-05-11
2 | Checking Customer API workflow | Done | 8 Hr | 2022-05-11 | 2022-05-12
3 | Testing API with Postman | Done | 3 Hr | 2022-05-12 | 2022-05-13
3 | Updating Customer Code Level Changes | In Progress (70%)_ | 5 Hr | 2022-05-12 | - | 5 Hr | 5 hr | NA | 3hr | 5hr | 6hr
4 | Updating Promo Code Table | Done | 4 Hr | 2022-05-15 | 2022-05-17 | 2022-05-16: 4hr
5 | Validating and re-building the solution | In Progress |  |  |  | 2022-05-16: 2 hr; 2022-05-17: 1hr